## Slide 1: Open Government Partnership Progress Report
June 2023 Report on Progress of Fourth National Action Plan Commitments

## Slide 2: 2.15-2.25pm: Commitment One
Presenters: Tula Garry Principal Advisor and Dean Rosson, Manager Integrity, Ethics and Standards, Te Kawa Maataho

## Slide 3: Commitment 1- Adopt the Policy Community Engagement Tool (PCET)
Lead Agency – Te Kawa Mataaho Public Service Commission
Commitment Description
Lift/improve the quality of community engagement by public service agencies for significant community engagement initiatives through the adoption of a common ‘tool’.
This will be achieved by:
The Public Service Commissioner issuing a model standard promoting the use of a common engagement tool for significant community engagement initiatives (consistency in approach and practice)
Reporting requirements within the model standard on engagement practice (this will be built in over time, a continuous improvement approach).
Leveraging the guidance created by the Policy Project (DPMC) and lessons learnt from piloting the Community Policy Engagement Tool (PCET) by agencies involved in the RCOI into the Mosque shooting in Christchurch
Strengthening capability across the Public Service via communities of practice and other initiatives, such as sharing good practice case studies.
Notes: We know that better quality community engagement will result in:
  Strengthened relationships and increasing trust between citizens, groups, communities and government
  Greater community participation and ability to influence govt policy and services design
  Richer input into planning and potential solutions
  Fairer more inclusive outcomes for all New Zealanders
Strengthening capability across the Public Service via communities of practice includes:
  Developing and disseminating best practices
  Access to resource and guidance material
  Training
  Sharing information
  Addressing knowledge gaps and
  Continuous improvement.

## Slide 4: Commitment 1
Progress
We have begun work on developing a Model Standard. The standard will refer agencies to guidance and resource material on community engagement practices to enable them to plan, deliver and evaluate community engagement.
Aspects of the model standard will be developed in consultation with stakeholders including agencies and CSOs. As part of this, “significant initiative” will be defined, along with reporting requirements.
We have engaged with the Ministerial Advisory Group Kāpuia on the tool and its application
Challenges
Ensure a pragmatic approach to the standard so that it is implemented effectively by agencies and supports changes in practice over time.
Next Steps
Further work on development of the standard, including consultation on threshold for application and reporting requirements.
Consider what other work including other communities of practice are required to raise capability in engagement practice.
Notes: FAQs 1. When will CSOs have the opportunity to have input into the development of the model standard? Our goal is to consult with civil society within the next few months.
2. How will you address community fatigue from agency engagement? We will do this through strengthening communities of practice and also help agencies with their planning and designing their community engagement initiatives. Better planning through use of the tool.
3. What support and resource will be provided to communities to undertake engagement? This is an agency responsibility- this will be determined by each respective agency when they are planning and designing their community engagement initiatives.
4. What support and resource will be provided to agencies for engagement? The model standard will direct agencies to the recommended engagement tool and resources for significant engagements. It is expected that each agency will determine the support and resources required as part of their planning process.
5. How will you establish effectiveness of engagement? This is an issue being thought through as part of the work on the reporting arrangements. The challenge is to get meaningful information from agencies and communities over time in an efficient and effective way. The first step will be via the introduction of a common approach for significant community engagement. Initial reporting will capture the level of engagement on the IAP2 spectrum and provide a benchmark on engagement level. Reporting will be built on over time to capture both quantitative and qualitative measures including stakeholder experience.
6. How does this align with Rec 38 (Social Cohesion) from the RCOI There is strong alignment. All RCOI recommendations including Rec 38 have been adopted by the Government. Rec 38 requires agencies to advise communities what level of engagement will be carried out with them in line with IAP2. It also encourages agencies to undertake more involve and collaborate levels of engagement. It is also likely that this definition will change over time as engagement practices evolve.
7. What if agencies and civil society have different views about what is a “significant” initiative?
Defining significant initiatives is yet to be completed. Any definition needs to consider a number of factors and some pragmatism may be required.

## Slide 5: Commitment 1 Question Time

## Slide 6: 2.25-2.35pm: Commitment Two
Presenter: Cathy Adank, Senior Advisor, Te Kawa Maataho

## Slide 7: Commitment 2 – Research deliberative processes for community engagement
Lead Agency – Te Kawa Mataaho
Commitment Description
Research how deliberative processes can be adapted to work well in a New Zealand content by identifying two examples and capturing lessons learned via case studies.
This will be done by:
Identifying at least two examples of deliberative processes.
Establishing a joint civil society/agency steering group to implement the commitment.
Evaluate lessons learned and publish results.
Identify future projects to use deliberative processes.
Goal – raise awareness of these processes, create tools and capability across government.
Research - how to these run overseas?
Created joint working group.
Looking at NZ examples – Watercare, MoT and Talanoa/Wānanga led by Ngāti Toa at Porirua.
Progress

## Slide 8: Commitment 2
Challenges
Case studies are good tools but they don’t create change by themselves. What else can we do to get agencies to try these types of processes? What are some “stretch” goals.
No funding – so we can’t run a deliberative process ourselves.
There are a lot of case studies to choose from in a NZ context.
Next Steps
Reach out to people to test if they’d be interested in being a case study.
Planning what these look like and how they can be presented.

## Slide 9: Commitment 2 Question Time

## Slide 10: 2.35-2.45pm: Commitment Four
Presenter: Tim Townsend, Manager, Counter Fraud and Strategy, Serious Fraud Office

## Slide 11: Commitment 4- Design and implement a National Counter Fraud and Corruption Strategy
Commitment Description
Progress

## Slide 12: Commitment 4
Challenges
Next Steps

## Slide 13: Commitment 4 Question Time

## Slide 14: 2.45-2.55pm: Commitment Five
Presenter: Thomas Abernethy, Senior Policy Advisor, MBIE

## Slide 15: Commitment 5- Increase transparency of beneficial ownership of companies and limited partnerships
Lead Agency – Ministry of Business, Innovation and Employment
Commitment Description
Increase the transparency of the beneficial ownership of New Zealand companies and limited partnerships by introducing legislation to make beneficial owners’ identifying information available on a public register.
Progress
Cabinet decisions were made at the end of 2021
Drafting instructions have been issued to PCO and work on the Corporate Role Holder Identifier Bill is ongoing
Policy team is working with operations (including the Companies Office) during drafting of legislation to help design implementation

## Slide 16: Commitment 5
Challenges
Drafting of the Bill has taken longer than anticipated due to resourcing constraints.
Planned milestones are indicative only as they are contingent on the Parliamentary process and passage of legislation
Operationalising legislation in a way that is effective and easy to use for government agencies and the public
Next Steps
Working with PCO to finalise draft legislation
Release of exposure draft of the Bill to the public and key stakeholders
Introduce the legislation to the House, and going through the legislative process
Design of policy and guidance documentation to support the introduction of the register
Develop publicity and information to support the enactment of the new legislation

## Slide 17: Commitment 5 Question Time

## Slide 18: 3.05-3.15pm: Commitment Six
Presenter: Olaf Buhrfeindt, Senior Policy Advisor and Rakesh Dushila, Manager Business Information and Analysis, NZ Government Procurement and Property

## Slide 19: Commitment 6- Improve govt procurement transparency
Lead Agency - The Ministry of Business, Innovation and Employment
Commitment Description
Improve the transparency of government sourcing activity and establish practices to better support capturing and sharing procurement information.​ To achieve this we are:
Making improvements to Government Electronic Tender Services (GETS) to better capture spend data in line with publication requirements under the Government Procurement Rules.
Developing the foundations of an integrated data system and future data management by establishing a data governance framework, reporting requirements and standards that will enhance the visibility of procurement information and enable a comprehensive view of government expenditure.
Developing a digital data platform to capture procurement information, in alignment with the Open Contracting Data Standard (OCDS).

## Slide 20: Commitment 6
Key progress
Completed current state and gap analysis of key datasets and master data stores, undertaken analysis to map our existing data model to OCDS, and developed a conceptual future state data model.
Completed workshops with agencies and suppliers to capture their desired data needs, and incorporated findings into requirements for a new one-stop shop Procurement Platform.
Completed scoping and design for changing manual tender responses by purchasing officers to improve data validation, accuracy, and traceability.
Challenges
Data collected in silos
Using different systems
Data Standards
Data availability
Quality of data
Indiscriminate data collation
Key next steps
Develop requirements for the digital data platform to meet OCDS standards.
Data Governance discovery and consultation design to establish data stewards for managing datasets on an ongoing basis.

## Slide 21: Commitment 6 Question Time

## Slide 22: 3.15-3.25pm: Commitment Three
Presenters: Colin Holden, General Manager, System Strategy and Tessa Houghton, Strategic Advisor , DIA

## Slide 23: Commitment 3- Establish a multi- channel approach to delivery of govt information and services
Lead agency - Department of Internal Affairs (DIA)
Commitment description
Establish and champion an all-of-government approach to the delivery of government information and services to ensure agencies deliver services that are accessible to and meet the diverse needs of all the people of Aotearoa.
This will be achieved through civil society organisations and government agencies working in partnership with, and leveraging, the Government Chief Digital Officer’s (GCDO) System Lead role for digital government transformation.
Agencies’ implementation of the approach will:
allow people to more easily access their entitlements and fulfil their obligations.
prevent the individual and societal costs experienced when people are unable to easily connect with services
enhance social inclusion and individual and community wellbeing.

## Slide 24: Commitment 3
Progress
We have identified options for progressing the ambition of the commitment through:
developing an all-of-government multichannel strategy or guidance, and/or
updating and championing the Digital Service Design Standard to improve clarity about requirements for the multichannel design and delivery of government services,
supporting agencies to use the approaches/resources developed, and developing and promoting case studies/examples of good practice.
Challenges
We need to bring in specialist expertise (engagement, channel strategy, service design) to progress this work.
The GCDO’s current funding and resourcing position is challenging, and we are still working through these challenges.
Next steps
Conclude conversations about managing our resourcing challenges and communicate timeframes and next steps.

## Slide 25: Commitment 3 Question Time

## Slide 26: 3.25-3.35pm: Commitment Seven
Presenters: Adam Carter, Policy Advisor, and Elisha Connell, Senior Policy Advisor, MoJ

## Slide 27: Commitment 7- Strengthen scrutiny of OIA exemption clauses
Commitment Description
To strengthen the scrutiny of legislative clauses that propose to override the disclosure requirements of the Official Information Act 1982.
This has the potential to:
Support policy makers
Increase transparency
Support good regulatory stewardship
Progress
Detailed project plan for the next year.
Begun identifying processes and guidance that prompt consideration of the applicability of the OIA.
We have had an initial conversation with the Office of the Ombudsman.
Notes: The Official Information Act 1982 (OIA) applies to a wide-range of public sector agencies. It provides ways for people to access official information, while recognising the need to protect official information to the extent consistent with the public interest.
OIA requests can be refused if making the information requested available would be contrary to a provision in another enactment.
Commitment 7 is about ensuring that when an OIA exception provision is being considered for new legislation, there is sufficient guidance and/or scrutiny relating to these provisions. By OIA exception provision we mean a new legislative provision that propose to override, in full or on part, some of the freedom of information requirements of the OIA.
This is a reasonably targeted commitment and is not a review of the OIA. However, the potential benefits of this work are:
  Supporting policy analysis. Ensuring agencies are giving due consideration to maintaining the integrity and purpose of the OIA, before they propose alternative disclosure regimes. In particular, supporting agencies to recognise the wide applicability of the OIA’s withholding grounds - whether conclusive or subject to the public interest.
  Increasing transparency. Ensuring that where an OIA exception provision is included in a Bill, that the justification is explicit and can easily be assessed during the Parliamentary process.
  Supporting good regulatory stewardship. If guidance is created, then it could set the foundation for future work. Guidance could support agencies to review any existing OIA exceptions in their current legislation in light of changing circumstances and operational experience, as part of their ongoing regulatory stewardship programmes.
Progress
Detailed project plan for the next year.
Begun identifying processes and guidance that prompt consideration of the applicability of the OIA - these include the LEG paper template, LDAC guidelines, disclosure statements, MoJ’s role.
We have had an initial conversation with the Office of the Ombudsman.

## Slide 28: Commitment 7
Challenges
Next Steps
Gather evidence
Develop options
Test proposals in targeted engagement later this year
Different kinds of OIA exception clauses which are not always easy to identify
Notes: Challenges
Scoping the project appropriately given the different kinds of OIA exceptions clauses
This can make identifying OIA exception clauses difficult
Next steps
Next few months involve examining how effective the current mechanisms are in supporting the scrutiny exception clauses. We know, for example, agencies may only become aware about the effects of a proposal on the OIA when legislation is being prepared. We will assess whether this is the appropriate place to improve scrutiny or whether there are opportunities earlier in the policy development phase. We will then look to identify some proposals that may be most effective including identifying the steps that are needed to make those changes.
From October we will start to firm up some options for targeted engagement towards the end of the year.
Although not something that was initiated directly as a result of this commitment, we note that the new Cabinet Manual 2023 highlights the Ombudsman’s role in this space, and it was updated to make it clearer that agencies should consult the Ombudsman on all legislative proposals that interact with the OIA. So that is already a positive step towards encouraging engagement earlier on in the process.
We will continue to look for opportunities to broaden engagement with other government and non-government organisations as the project develops.
Happy to take any questions.

## Slide 29: Commitment 7 Question Time
Notes: FAQs
Why are you not doing an OIA review?
In 2019, the Ministry of Justice undertook public consultation on the Act and provided the Government with advice on its recommendations for a review. The Minister chose not to progress a review due to other priorities in the portfolio.
Why can't you look at retrospective OIA exemption clauses?
One of our commitments for next year is to explore the potential inclusion of reviewing existing exemption clauses in the future.
We envisage any examination of existing exception clauses will be the responsibility of individual agencies. If we develop guidance as a result of the work underway, we intend to circulate this to agencies and encourage them to apply the guidance as part of their regulatory stewardship of the legislation they are responsible for.
How will civil society be involved in this process?
We are planning to have opportunities for engagement later this year after the initial research has been completed.
The existing tools and processes (like LDAC guidelines) aren’t strong enough. How are you going to strengthen these?
Part of the review phase is looking at the way we could make a potential change. Options for how to strengthen the guidelines will be considered as this work progresses.
What are the reasons for the government to use OIA exemption clauses?
Clauses take a number of different forms. Part of the review phase is looking at the range of rationales for using such clauses. This will help us in developing principles that could be used to support agencies considering including any such clauses in their regulatory regime,
Are we considering ways for the public to be involved in proposals before they are introduced to parliament?
There is a convention that legislative proposals remain confidential until Cabinet has made decisions. However, there may be room for agencies to make any anticipated impacts on the OIA explicit during consultation on policy proposals.
We are looking at ways to ensure that where an OIA exception provision is included in a Bill that its inclusion and rationale is clearly articulated. This could help the public provide considered feedback when the Bill is considered at select committee. There are some existing tools that do that have a role in making certain policy and legislative considerations explicit such as Departmental Disclosure Statements or Regulatory Impact Statements.
We will have a better answer to this question once the first phase of the review is completed.
Do we believe OIA exceptions have been used too much?
We are still in the early stages of this work, but don’t have evidence for this at this stage. We are also mindful of the scope of this work and that this falls outside the focus of this project.
During this project we won’t be looking at:
  whether exception clauses have been used in excess
  whether they should be used less often or more narrowly in the future
  assessing the application of exception clauses in the context of OIA requests.

## Slide 30: 3.35-3.45pm: Commitment Eight
Presenter: Jocelyn Morrison, Principal Advisor Statistics NZ

## Slide 31: Commitment 8 - Improve transparency and accountability of govt algorithm use
Lead agency – Stats NZ
Commitment Description
This commitment aims to improve the support available to government agencies to enable them to implement the principles in the Algorithm Charter and provide greater transparency and accountability of algorithm use across government.
Progress
We have:
Established a community of practice for Algorithm Charter signatories to share ideas and advice, discuss pain points, compare ‘what works’, and develop support resources.
Started developing assessment tools and a user guide to help agencies assess the risks and potential impact of the algorithms they are designing or using.
Published our high-level phased approach to implementing the recommendations from the One Year Review on data.govt.nz.

## Slide 32: Commitment 8
Phased approach to implementation
Phase 1: Strengthening guidance and best practice Supporting government agencies to develop, use, and maintain algorithms in a safe and ethical way.
  Developing algorithm threshold and impact assessment tools
  Establishing a community of practice
Phase 2: Engagement with iwi and Māori, civil society organisations and the public To provide greater visibility and transparency and inform actions.
  Improving transparency of agency practices
  Providing practical engagement advice to agencies
Phase 3: Greater oversight and governance Transforming oversight, governance, monitoring, and assurance.
  Exploring regulatory approaches
  Embedding governance and monitoring

## Slide 33: Commitment 8
Challenges
The rapid development of new technologies such as machine learning and generative AI, and the extent to which these may use algorithms.
Understanding the Charter changes needed to reflect the Māori Data Governance Model.
Aligning with the generative AI guidance developed for agencies.
Next Steps
Seek signatory and public feedback on the algorithm assessment tools and user guide.
Seek expert advice to incorporate te ao Māori perspectives into the assessment tools.
Provide secretariat support to the Community of Practice.

## Slide 34: Commitment 8 Question Time

## Slide 35: Send any additional questions to:
ogpnz@publicservice.govt.nz
We will respond to all questions raised and post the responses on the OGP website ogp.org.nz

## Slide 36
Waiata Te Aroha
Te aroha
Te whakapono
Me te rangimarie
Tatou Tatou e Love, hope, peace, for us all